## Slide 1
OFFICIALS EDUCATION Endurance Level 1 – 3
LEVEL 3
Self-Paced Module
COURSE DIRECTOR
February 2026_01/02/2026

## Slide 2
COURSE DIRECTOR
The Course Director role is not one that is covered in L1 Endurance Officials’ training, but it is a role that Officials must work with.
This module provides an understanding of the Course Directors duties.

## Slide 3
COURSE DIRECTOR: CONTENTS
Roles and Responsibilities
Resources
Phases of Preparation
  Pre-Event
  Race Day
  Post Race

## Slide 4
Roles & Responsibilities 1
The Course Director is responsible for the safe management of all activities on the course.

## Slide 5
Roles & Responsibilities 2
Here are some of the key roles we have identified ….
Implementation of action points (or control measures) specified for the course route in the Event Safety (or Management) Plan, arising out of the event Risk Assessment.
Setting out the course - according to the Course Measurement Record.
Supervising erection (and subsequent removal/ recovery) of course route signage.

## Slide 6
Roles & Responsibilities 3
Further key roles we have identified ….
Supervising traffic management (where appropriate), managing interactions between competitors and vehicles and / or pedestrians and other road users.
Monitoring the deployment of on course first aid and medical resources.
Supervising the setting up, staffing and break down of on course drink (and sponge) stations.

## Slide 7
Roles & Responsibilities 4
Further key roles we have identified ….
Liaison with police deployed on the course route – if applicable.
Managing course route communications.
Briefing of sector (course route) marshals.
Checking the course route is clear of obstructions.
Ensuring competitors follow the marked course, avoiding both shortcuts and diversions.
Supervising course route clearance, recovery of equipment, litter picking, refuse collection.

## Slide 8
Roles & Responsibilities 5
In most races implementation of specific tasks will be delegated to individual marshals (or contractors as appropriate), leaving the Course Director responsible for overall supervision and co-ordination.
In smaller races the tasks of the Course Director may be carried out by the Race Director and sector marshals or individual marshals, without any one person being designated to carry out this specific role.

## Slide 9
Roles & Responsibilities 6
In larger races the tasks of the Course Director may be divided between mobile units travelling in advance and behind, sector marshals, separate event Traffic and Medical Controls and facilities teams.
There are significant benefits in having a single person with overall responsibility for all activities on the course route. Even if specific tasks are delegated to designated marshals, volunteers or contractors the need for overall co-ordination remains.

## Slide 10
Roles & Responsibilities 7
The Course Director will need a detailed understanding of all course route activities, team briefings, event timings and safety measures plus contact details for all key personnel and background knowledge of other event activities (e.g. start / finish or ancillary events, fun run, etc.).
Clear communications and reporting structures plus contingency plans should be agreed in advance for key events such as readiness for race start, monitoring progress of runners and stand down of volunteers, plus accident reporting and emergency procedures.
Previous knowledge of the event (for instance as a sector marshal or shadowing the course director in previous years) and/or experience of working in similar capacity at other events will be valuable.

## Slide 11
Resources 1
Event Management Plan Resources:
Copy of the traffic management and marshalling plan.
Copy of the event safety plan and contingency plan.
Copy of the course measurement report.
Copy of the course route facilities plan (first aid, toilets, drinks / sponge stations, signage).
Details of any special arrangements to ensure access to / from adjoining properties.
Arrangements for course de-rigging, refuse collection and disposal.

## Slide 12
Resources 2
Race-day Resources:
Suitable clothing, depending on weather and activities to be undertaken, including high visibility (to BSEN 471) if working on or adjacent to an open highway.
Transport for yourself, plus assistant (if required).
Event passes (if required).
Event radio, mobile phone (as applicable).
Race Day contact details for all key personnel, first aid and emergency services.
Keys required for access to land or property.

## Slide 13
Resources 3
Additional Race-day Resources:
Other equipment, depending on the circumstances of your race may include:
Spare equipment for marshals: radios, radio batteries, signage, cones, barrier tape, loudhailers, etc.
Equipment for competitors: space blankets, bottled water, energy drinks, etc.

## Slide 14
Phases of Preparation 1
We will look at preparation in three phases:
Pre-Event
Race Day
Post Race

## Slide 15
Phases of Preparation 2
Traffic Management:
Note: the term ‘traffic management’ refers to a variety of temporary traffic arrangements to ensure safe segregation of competitors, motorists, pedestrians and other highway users (cyclists, horses, etc).
Measures include full road closures, partial (i.e. lane) closures, temporary traffic lights, one-way traffic, etc., effected by a combination of diversion signage, cones, barriers, etc.
In some cases, these measures will be implemented by volunteer marshals; other highways authorities may insist on the use of qualified highways contractors.
‘Highways’ include roadways, pavements, footpaths, bridleways, etc.

## Slide 16
Phases of Preparation 3
Pre-Event:
Liaise with Race Director. Familiarising yourself with the course route, traffic conditions, traffic management, marshalling, facility (first aid, toilets, drinks / sponge stations, signage, refuse collection/disposal) event Safety and Contingency Plans, including welfare arrangements (toilets, food and shelter) for volunteers, plus de-brief notes from previous years.
Ensure that liaison has been carried out with the highways and Local Authority, police and adjoining property owners. Where keys are required for access to land or property these should be collected before race day if possible. Special arrangements may have been made to ensure access to adjoining properties.

## Slide 17
Phases of Preparation 4
Pre-Event (Continued):
Obtain race day contact details for all key personnel, first aid and emergency services.
Supervise the briefing of sector marshals and course drinks / sponge station, course route signage erection / recovery and refuse collection/disposal teams, plus arrangements for delivery of essential equipment – signage, barriers, cones, radios, loudhailers etc.
Check the course-wide communications to identify ‘dead spots’ for mobile phone and/or radio reception. Where repeater stations are used to overcome radio ‘dead spots’ these should be set up and tested in position before race day. Note that atmospheric conditions and the presence of large crowds can adversely affect radio transmissions on race day.

## Slide 18
Phases of Preparation 5
Pre-Event (Continued):
Check the course route against the Course Measurement Record - the detailed description of the measured course prepared by the course measurer when the original measurement is prepared, usually in a map and text form.
Where road closures and/or parking suspensions and tow aways are to be employed, the Local Authority will normally require erection, weekly inspection and certification of advance warning signs. In some cases, this can be done by event volunteers, other authorities will require qualified highways contractors if permitted by LA.
Advance-warning leaflets may also need to be delivered to adjoining properties.

## Slide 19
Phases of Preparation 6
Pre-Event (Continued):
Check that the course route is clear of obstructions, parked vehicles (where applicable), builders skips, roadworks, etc. in the weeks and days before the event.
Liaise with the Highways Authority, contractors, property owners etc. regarding the removal of any obstructions discovered or ensuring that protection / diversions are provided around the remaining obstructions.

## Slide 20
Phases of Preparation 7
Race Day:
Report your arrival to the designated person. This may be the Race Director or event control.
Collect any essential equipment – radio, loudhailer, etc.
It is good practice for the Course Director to have an assistant to action immediate tasks or handle phone/radio calls when the Course Director is engaged on other duties.
In some cases, it may be appropriate for the Course Director to be deployed in a lead vehicle, or safety car travelling ahead of the race leaders.
Supervise setting out of the course according to the Course Measurement Record; including delivery of essential on-course equipment (barriers, cones, toilets, etc.) and erection of course route signage.

## Slide 21
Phases of Preparation 8
Race Day (Continued):
Carry out final inspection of course route for obstructions and either arrange for removal or protection/diversions to be provided around remaining obstructions. Continue monitoring throughout the event.
Ensure implementation of any special arrangements to ensure access to adjoining properties, pedestrian crossing points, etc.
Check with Managers of on-course drink/sponge stations, toilets, entertainment points etc. that all are properly set up, stocked and manned. If no appointed Managers, the Course Director would need to supervise.
Monitor deployment of on-course first aid and medical resources.
Liaise with police deployed on the course route – if applicable.

## Slide 22
Phases of Preparation 9
Race Day (Continued):
Check Chief/Sector Marshals and course route marshals' attendance (plus delivery/collection of essential equipment) and confirm their readiness for implementation of road closures or traffic management (where relevant), stewarding/directing runners and spectators/pedestrians around the course.
Agree re-deployment of marshals as necessary to resolve shortfalls in attendance or additional identified hazards/ measures.
Sufficient time should be allowed for final course sign off so that notification of any delay can be given to runners before they assemble for the race start.

## Slide 23
Phases of Preparation 10
Race Day (Continued):
Manage the course route communications (mobile phone and/or shortwave radio) and decision making on the day.
Supervise monitoring and reporting on race progress.
Maintain a log of incidents and timings occurring during the event (plus photos/video where appropriate), to assist the de-brief process and any formal accident/incident reports.
Implement course route clearance, lifting traffic and crowd/ pedestrian management (where relevant), recovery of equipment, signage, litter picking, refuse collection, etc.
Clear marshals and medical team’s stand-down with the Race Director, leading to final sign off after the last finishers.
Confirm your stand down and return any equipment before departure.

## Slide 24
Phases of Preparation 11
Post-Race:
Ensure the collation and return of attendance records, debrief reports and expenses claims for all course route volunteers (and contractors) if applicable.
Provide a post-race debrief report on the course route management, including a review of the course route safety measures identified in the event risk assessment.

## Slide 25
End of Module Questions
End of module questions must be completed by the candidate, with answers inserted on your Self-Paced Module Return Form.
You may need to complete some additional research to assist you in answering and justifying your answers to the questions for this module.

## Slide 26
Course Director – Questions 1
What is the Course Directors principal role? (1 mark)
List at least 5 of the Course Directors key responsibilities. (5 marks)
What are the main differences between the role of the Course Director of smaller and larger races? (2 marks)
Note 3 examples of the detailed understanding a Course Director needs of the race. (3 marks)
What experience should the Course Director have? (1 mark)
List at least 3 Race-day resources the Course Director needs to fulfil their role. (3 marks)
Which of following is not part of the pre-race preparation for a Course Director? (1 mark)
Supervising Sector Marshal briefings.
Checking course wide communications.
Ensuring collation of final attendance records.
Course route checks against the course measurement.

## Slide 27
Course Director – Questions 2
Under which of the Pre-Event, Race Day or Post-Race Phases of Preparation would you class the following:
Monitor deployment of on-course first aid and medical resources. (1 mark)
Collate and return attendance records. (1 mark)
Supervise setting out of the course. (1 mark)
Obtain race day contact details for all key personnel, first aid and emergency services. (1 mark)
What does LA stand for? (1 mark)
Throughout the module, many of the key interfaces for the Course Director are identified, list at least 5 you have come across in your study of the module. (5 marks)
What is the correct protocol to follow where road closures and/or parking suspensions and tow-aways are to be employed? (1 mark)

## Slide 28
Course Director – Questions 3
When setting out the course, what should be used to ensure this is accurately completed? (1 mark)
What does traffic management refer to? (1 mark)
List at least 3 Event Management Plan resources the Course Director needs to fulfil their role. (3 marks)
Note 3 items of spare equipment a Course Director should be prepared with in the event of part of the course markings being breached. (3 marks)
How do you ensure that all directional arrows and kilometre markers are in the correct place?
Note the 2 key resources required. (2 Marks)
List at least 3 procedures to be followed. (3 Marks)
Total marks = 40, Pass mark = 32 (80%)